## Instructions for Work Plan
Instructions and Guidance for preparing the Work Plan and Budget
Background
According to RCW 36.78.121, Counties shall annually submit their maintenance plans to the County Road Adminstration Board.
WAC 136-11 provides guidance and information regarding compliance with the Maintenance Management Standard of Good Practice.
The specific requirement for preparation of the Work Program (Plan) and Budget is that it is based upon the road features to be
maintained, the types and amount of maintenance work planned and the costs for the labor, equipment and materials needed
to complete the work.
Preparation of the Work Plan and Budget
In this Excel spreadsheet file, worksheets have been developed to guide preparation of a work plan and budget.
The sample shown in the worksheet follows the typical maintenance management format for a work program and budget.
Note that counties may also use the ouptut of a Maintenance Management System instead of the spreadsheet. A number of
counties use the WinCAMS Maintenance Management module. Preparing a Work Program and Budget from the reports
function of this module satisfies the requirement for a work plan and budget under the standard of good practice.
Counties also have the option of preparing a narrative form of work plan and budget. However, this narrative must include
the inventory of road features maintained, the type and amount of work planned and the costs for labor, equipment and materials,
as required under WAC 136-11, the standard of good practice for maintenance management.
For preparation of the Work Plan and Budget using the spreadsheet provided in this file, select the Interactive Work Plan & Budget
worksheet. Samples of typical maintenance activities are shown on this sheet. (1) Use the activity codes and names that your county
uses on timecards and budget documents. (2) Fill in the quantity of inventory that the work activity is performed on. (3) Fill in
the planned effort level--this identifies how much work (in work units) is planned for each unit of inventory.
From he inventory and effort level, the annual work quantity is calculated. (4) Enter the average daily production and crew size
in the identified columns. (5) Enter the costs per crewday for labor, equipment and materials. A total cost (budget) is calculated.
The spreadsheet also provides a calculation for the percentage of the budget for each activity. See the sample spreadsheet
for guidance on the preparation of the work plan and budget.
A spreadsheet has also be developed that includes a column for the percent of planned work. By entering percentages in this
column, you can see the effects on the budget for planning to do more or less than the planned amount of work.

## Work Plan & Budget Definitions
Work Plan and Budget Calculations and Descriptions
| Column: | Calculations | Description
Annual Work Qty | H | = C X E X G | Inventory x Effort Level = Annual Work Quantity
Person Days | K | = ( H / I ) X J | (Annual Work Quantity / Average Daily Production) x Crew Size
Labor Budget | M | = ( H / I ) X L | Crew Days x Labor Cost Per Day = Labor budget
Equipment | O | = ( H / I ) X N | Crew Days x Equip Cost Per Day = Equipment budget
Materials | Q | = ( H / I ) X P | Crew Days x Material Cost Per Day = Materials budget
Total Cost | R | = M + O + Q | Labor + Equip. + Materials = Total Cost

## Interactive Work Plan & Budget
WORK PROGRAM AND BUDGET REPORT
COUNTY ROAD ADMINISTRATION BOARD
Maintenance Management Program
Lewis County - Planned for 2015
|  | C | D | E | F | H | I | J | K | L | M | N | O | P | Q | R | S
(COST DISTRIBUTION)
[6 empty] | ANNUAL | AVG |  |  | Labor |  | Equip |  | Material
| ACTIVITY |  |  | PLANNED |  | WORK | DAILY | CREW | PERSON | cost per |  | cost per |  | cost per | MATERIAL/ OTHER | TOTAL | Percent
CODE | NAME | INVENTORY |  | EFFORT LEVEL |  | QTY | PROD | SIZE | DAYS | crewday | LABOR | crewday | EQUIP | crewday |  | COST | of Total
|  | QTY | UNIT | QTY | UNIT | = ( C X E ) |  | = ( H / I ) X J |  |  | = ( H / I ) X L | = ( H / I ) X N |  | = ( H / I ) X P |  | = M+O+Q
2301 | Seal Coating | 1044.799 | MI | 894.0191 | SY | 934070.2617 | 40000 | 22 | 513.7386 | 5433.6 | 126884.1043 | 6490.09 | 151555.0016 | 58080.34 | 1356277.9595 | 1634717.0655 | 13.46% | 1634717.15 | -0.084515
2302 | Fog Seal | 1044.799 | MI | 13.068 | SY | 13653.4333 | 1000 | 8 | 109.2275 | 1919.02 | 26201.2116 | 1446.69 | 19752.2855 | 1329.63 | 18154.0146 | 64107.5117 | 0.528% | 64107.65 | -0.13834
2303 | Haul to Stockpile | 10500 | TN | 0.5267 | TN | 5530.35 | 300 | 5.6 | 103.2332 | 1421.76 | 26209.4347 | 2809.04 | 51783.2479 | 0 | 0 | 77992.6826 | 0.6424% | 77987.75 | 4.9326
2304 | Brooming | 2089.598 | SM | 3.4253 | PM | 7157.5 | 42 | 2.2 | 374.9167 | 554.93 | 94569.3212 | 952.28 | 162284.384 | 0 | 0 | 256853.7052 | 2.115% | 256850.15 | 3.5552
2307 | Crack Sealing | 1044.799 | MI | 15.5445 | POUNDS | 16240.8781 | 600 | 5 | 135.3407 | 1076.96 | 29151.2934 | 804 | 21762.7766 | 1181.79 | 31988.8455 | 82902.9154 | 0.6828% | 82903.2 | -0.28456
2308 | Dust Control | 46.293 | MI | 64.2963 | GAL | 2976.4686 | 500 | 5.25 | 31.2529 | 1298.74 | 7731.3177 | 1363.28 | 8115.5203 | 495.89 | 2952.002 | 18798.84 | 0.1548% | 18798.83 | 0.010014
2309 | Graveling | 46.299 | MI | 0.7948 | MI | 36.7984 | 1 | 4.2 | 154.5535 | 977.51 | 35970.8482 | 1843.82 | 67849.7092 | 2309.35 | 84980.4894 | 188801.0468 | 1.555% | 188808.79 | -7.7432
2310 | Grading | 46.293 | MI | 20.6359 | PM | 955.2977 | 10 | 2 | 191.0595 | 468.48 | 44753.7875 | 626.05 | 59806.4137 | 0 | 0 | 104560.2012 | 0.8612% | 104559.87 | 0.3312
2311 | Grading-Shoulder Trimming, General | 2089.706 | SM | 0.072 | SM | 150.4588 | 6 | 7.8 | 195.5965 | 1887.76 | 47338.3608 | 2443.41 | 61272.1024 | 0 | 0 | 108610.4632 | 0.8945% | 108568.01 | 42.4532
2312 | Cold Mix Patching - Manual | 1044.799 | MI | 1.6773 | HR | 1752.4414 | 22 | 2.55 | 203.1239 | 596.52 | 47516.651 | 667.99 | 53209.6957 | 327.38 | 26077.9206 | 126804.2673 | 1.044% | 126799.79 | 4.4773
2313 | Hot Mix Patching | 1044.799 | MI | 7.1022 | TN | 7420.3715 | 300 | 9.4 | 232.505 | 2201.93 | 54463.7951 | 4008.71 | 99153.7242 | 20735.31 | 512879.0083 | 666496.5276 | 5.489% | 666499.12 | -2.5924
2315 | Dig Outs | 1044.799 | MI | 1.5808 | HR | 1651.6183 | 76.8 | 7.8 | 167.7425 | 1764.63 | 37949.1553 | 1738.76 | 37392.8094 | 801.03 | 17226.5075 | 92568.4722 | 0.7624% | 92565.7 | 2.7722
2317 | Other Roadside Maint / Road Patrol | 1044.799 | MI | 4.7546 | HR | 4967.6013 | 17.6 | 2 | 564.5002 | 524.4 | 148011.9395 | 150 | 42337.5113 | 1.77 | 499.5826 | 190849.0334 | 1.572% | 190849.07 | -0.03658
2320 | Shoulder Rebuilding | 2089.706 | SM | 0.0134 | SM | 28.0021 | 0.5 | 4 | 224.0165 | 825.3 | 46220.2009 | 1344.29 | 75285.7796 | 447.39 | 25055.6836 | 146561.6641 | 1.207% | 146236.61 | 325.0541
2402 | Ditch Cleaning - Excavator/Grader | 2089.706 | SM | 0.0922 | DM | 192.6709 | 0.96 | 5.8 | 1164.0533 | 1231.03 | 247066.3017 | 1616.75 | 324479.861 | 0 | 0 | 571546.1627 | 4.707% | 571572.21 | -26.0473
2403 | Culvert Cleaning | 5819 | EA | 0.1707 | EA | 993.3033 | 20 | 4 | 198.6607 | 916.24 | 45505.2108 | 648 | 32183.0269 | 0 | 0 | 77688.2377 | 0.6399% | 77697.04 | -8.8023
2404 | Culvert Repair / Replacement | 5819 | EA | 1.4944 | FT | 8695.9136 | 60 | 5 | 724.6595 | 1056.24 | 153082.863 | 1462 | 211890.4281 | 270.47 | 39199.7292 | 404173.0203 | 3.329% | 404176.29 | -3.2697
2409 | Catch Basin Cleaning | 256 | EA | 1 | EA | 256 | 26.6 | 3 | 28.8722 | 522.47 | 5028.2827 | 729.34 | 7019.212 | 0 | 0 | 12047.4947 | 0.09923% | 12047.5 | -0.0052632
2410 | System Inventory / Marking | 5819 | EA | 0.1303 | HR | 758.2157 | 17.6 | 2 | 86.1609 | 280 | 12062.5225 | 84 | 3618.7567 | 0 | 0 | 15681.2792 | 0.1292% | 15687.18 | -5.9008
2411 | Other Drainage Maintenance | 1044.799 | MI | 1.4357 | HR | 1500.0179 | 17.6 | 6 | 511.3697 | 1308.08 | 111485.4231 | 1632 | 139092.5712 | 167.79 | 14300.455 | 264878.4492 | 2.182% | 264874 | 4.4492
2502 | Bridge Cleaning / Minor Painting | 208 | EA | 4.0545 | HR | 843.336 | 20 | 2 | 84.3336 | 545.1 | 22985.1227 | 200.39 | 8449.8051 | 0 | 0 | 31434.9277 | 0.2589% | 31435 | -0.072268
2503 | Other Bridge Maintenance | 208 | EA | 4.5529 | HR | 947.0032 | 44.5 | 5 | 106.4049 | 1097.68 | 23359.696 | 524 | 11151.2287 | 704.85 | 14999.8923 | 49510.817 | 0.4078% | 49511.25 | -0.43304
2504 | Bridge Rail Repair | 14801 | FT | 0.0144 | FT | 213.1344 | 50 | 5 | 21.3134 | 1097.68 | 4679.0674 | 1304 | 5558.5452 | 259.9 | 1107.8726 | 11345.4851 | 0.09344% | 11323.41 | 22.0751
2601 | Paths/Trails Maintenance | 20 | HR | 1 | HR | 20 | 4 | 2 | 10 | 100.74 | 503.7 | 22.4 | 112 | 0 | 0 | 615.7 | 0.005071% | 615.68 | 0.02
2602 | Snow/Ice Control - Plow/Sand | 1044.799 | MI | 4.2113 | HR | 4399.962 | 64.8 | 8 | 543.2052 | 2104.33 | 142885.3718 | 4392.87 | 298278.7222 | 959.63 | 65159.4994 | 506323.5934 | 4.17% | 506327.08 | -3.4866
2603 | Snow/Ice Control - Anti Icing | 1044.799 | MI | 0.4786 | HR | 500.0408 | 8 | 2 | 125.0102 | 524.4 | 32777.6745 | 330 | 20626.6831 | 0 | 0 | 53404.3576 | 0.4398% | 53399.24 | 5.1176
2606 | Dead Animal Disposal | 1044.799 | MI | 0.5519 | HR | 576.6246 | 4.45 | 0.5 | 64.7893 | 97.96 | 12693.5152 | 28 | 3628.1995 | 1.93 | 250.0866 | 16571.8014 | 0.1365% | 16572.53 | -0.72865
2607 | Sign Inspection / Cleaning / Maint | 11853 | EA | 1.1463 | EA | 13587.0939 | 250 | 2 | 108.6968 | 280 | 15217.5452 | 224 | 12174.0361 | 0 | 0 | 27391.5813 | 0.2256% | 27391.72 | -0.1387
2608 | Sign Maintenance: Routine | 11853 | EA | 0.3164 | EA | 3750.2892 | 10 | 3 | 1125.0868 | 664.4 | 249169.2144 | 252 | 94507.2878 | 95 | 35627.7474 | 379304.2497 | 3.124% | 379274.21 | 30.0397
2609 | Sign Maintenance: Vandalism | 11853 | EA | 0.0844 | EA | 1000.3932 | 7 | 1.25 | 178.6416 | 297.2 | 42473.837 | 56 | 8003.1456 | 57.51 | 8218.9447 | 58695.9273 | 0.4834% | 58671.76 | 24.1673
2610 | Striping - Centerline | 811.0811 | MI | 0.4969 | MI | 403.0262 | 7 | 2.5 | 143.9379 | 528.12 | 30406.5994 | 768 | 44217.7315 | 2340 | 134725.9007 | 209350.2316 | 1.724% | 209367.57 | -17.3384
2611 | Striping - Edgeline | 1458.1458 | MI | 0.5823 | MI | 849.0783 | 20 | 2.5 | 106.1348 | 528.12 | 22420.7616 | 768 | 32604.6067 | 2339.99 | 99341.7365 | 154367.1048 | 1.271% | 154378.39 | -11.2852
2612 | Guardrail Repair | 261577 | FT | 0.0016 | FT | 418.5232 | 60 | 6 | 41.8523 | 1370.16 | 9557.3958 | 977.94 | 6821.5096 | 1411.76 | 9847.5719 | 26226.4773 | 0.216% | 26632.35 | -405.8727
2613 | Other Guardrail Maintenance | 261577 | FT | 0.0006 | HR | 156.9462 | 40.05 | 4.5 | 17.6344 | 951.03 | 3726.855 | 391.19 | 1532.9784 | 0 | 0 | 5259.8334 | 0.04332% | 5026.71 | 233.1234
2614 | Replace / Install Guidepost | 2089.706 | SM | 0.0718 | EA | 150.0409 | 2 | 0.4 | 30.0082 | 104.88 | 7868.1443 | 22.4 | 1680.458 | 25 | 1875.5111 | 11424.1134 | 0.09409% | 11420.5 | 3.6134
2616 | Street Sweeper | 1044.799 | MI | 0.3828 | PM | 399.9491 | 10 | 1.5 | 59.9924 | 398.48 | 15937.17 | 802.41 | 32092.3123 | 0 | 0 | 48029.4823 | 0.3956% | 48034.42 | -4.9377
2618 | Street Lighting | 34 | EA | 0 | HR | 0 | 0.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0.04942% | 6000 | 0
2619 | Pavement Markings | 397 | EA | 0.5038 | EA | 200.0086 | 6 | 3 | 100.0043 | 552.56 | 18419.4587 | 168 | 5600.2408 | 198.01 | 6600.6171 | 30620.3166 | 0.2522% | 30517.41 | 102.9066
2620 | Other Misc Traffic Maintenance | 1044.799 | MI | 0.2393 | HR | 250.0204 | 12.75 | 1.5 | 29.4142 | 332.2 | 6514.257 | 168 | 3294.3865 | 3825.15 | 75009.0616 | 84817.7051 | 0.6986% | 84807.49 | 10.2151
2704 | Chem Veg Ctrl-Shoulder Sterilize | 2089.598 | SM | 1.6467 | AC | 3440.941 | 30 | 3.4 | 389.9733 | 846 | 97034.537 | 360 | 41291.2923 | 309.5 | 35499.0416 | 173824.8709 | 1.432% | 173827.77 | -2.8991
2705 | Chem Veg Ctrl-Brush | 2089.598 | SM | 0.1675 | AC | 350.0077 | 15 | 4 | 93.3354 | 825.13 | 19253.455 | 360 | 8400.184 | 1521.47 | 35501.7441 | 63155.3831 | 0.5202% | 63152.31 | 3.0731
2706 | Chem Veg Ctrl-Dormant | 2089.598 | SM | 0.0479 | AC | 100.0917 | 5 | 4 | 80.0734 | 825.14 | 16517.9404 | 360.01 | 7206.8058 | 1775.18 | 35536.1725 | 59260.9186 | 0.4881% | 59200.58 | 60.3386
2708 | Slope Reseeding-Hydroseeding | 2089.598 | SM | 0.0208 | AC | 43.4636 | 1 | 4 | 173.8546 | 804.49 | 34966.0625 | 1068.12 | 46424.3814 | 115.1 | 5002.6648 | 86393.1087 | 0.7116% | 86345.99 | 47.1187
2720 | Brush Cutting-Area Shops | 1044.799 | MI | 5.6303 | HR | 5882.5318 | 26.76 | 3 | 659.4767 | 664.32 | 146034.5117 | 350.39 | 77024.6757 | 161.49 | 35499.6286 | 258558.8159 | 2.13% | 258561.75 | -2.9341
2721 | Roadside Mowing/Brush Cut - Machine | 2089.598 | SM | 2.5411 | SM | 5309.8775 | 11 | 2.45 | 1182.6545 | 553.76 | 267308.8866 | 1242.8 | 599919.6118 | 0 | 0 | 867228.4983 | 7.143% | 867237.66 | -9.1617
2723 | Canopy Clearing | 2089.598 | SM | 0.0225 | SM | 47.016 | 0.5 | 8 | 752.2553 | 1832.44 | 172307.8332 | 743.98 | 69957.8604 | 10.62 | 998.6189 | 243264.3124 | 2.004% | 243647.68 | -383.3676
2724 | General Litter/Garbage Pickup | 1044.799 | MI | 0.0957 | HR | 99.9873 | 0.88 | 0.6 | 68.1731 | 128.32 | 14579.9611 | 11.2 | 1272.5652 | 748.07 | 84997.1282 | 100849.6545 | 0.8306% | 100852.72 | -3.0655
2726 | Stump Grinding | 1044.799 | MI | 0.5168 | HR | 539.9521 | 32 | 4 | 67.494 | 825.09 | 13922.1593 | 707.98 | 11946.1033 | 0 | 0 | 25868.2625 | 0.2131% | 25870.04 | -1.7775
2904 | General Training | 14016 | HR | 0.2073 | HR | 2905.5168 | 72.5 | 10 | 400.7609 | 2582.44 | 103494.1077 | 137.79 | 5522.085 | 259.5 | 10399.7463 | 119415.939 | 0.9835% | 119419.36 | -3.421
2905 | Equipment Certification Training | 12264 | HR | 0.2277 | HR | 2792.5128 | 8 | 2.25 | 785.3942 | 433.36 | 151270.4184 | 0 | 0 | 0 | 0 | 151270.4184 | 1.246% | 151286.65 | -16.2316
2907 | Safety Meetings/Safety Supplies | 14016 | HR | 0.1198 | HR | 1679.1168 | 10 | 1.01 | 169.5908 | 259.68 | 43603.3051 | 17.89 | 3003.94 | 226.24 | 37988.3385 | 84595.5835 | 0.6967% | 84653.25 | -57.6665
2909 | Maint Supervisor/Admin Functions | 14016 | HR | 1.9481 | HR | 27304.5696 | 13 | 1.63 | 3423.573 | 482.15 | 1012684.4794 | 101.89 | 214004.8151 | 111.89 | 235008.3302 | 1461697.6247 | 12.04% | 1461673.16 | 24.4647
2910 | Road Approach Permits | 8760 | HR | 0.0354 | HR | 310.104 | 2.4 | 0.31 | 40.0551 | 160.14 | 20691.6894 | 0 | 0 | 0 | 0 | 20691.6894 | 0.1704% | 20683.92 | 7.7694
2911 | Equipment Service/Repair-Field | 12264 | HR | 0.0171 | HR | 209.7144 | 1.71 | 0.19 | 23.3016 | 57.05 | 6996.612 | 0 | 0 | 0 | 0 | 6996.612 | 0.05763% | 7005.67 | -9.058
2912 | Shop/Yard Maintenance | 12264 | HR | 0.4277 | HR | 5245.3128 | 8 | 1.56 | 1022.836 | 418.91 | 274664.2481 | 0 | 0 | 154.79 | 101490.246 | 376154.4942 | 3.098% | 376185.55 | -31.0558
2915 | Leave Time Taken | 14016 | HR | 2.2253 | HR | 31189.8048 | 8 | 1.21 | 4717.458 | 305.96 | 1192854.0846 | 0 | 0 | 0 | 0 | 1192854.0846 | 9.825% | 1192866.46 | -12.3754
2916 | Other Admin/Medical Testing | 14016 | HR | 0.1283 | HR | 1798.2528 | 17.25 | 0.89 | 92.7794 | 230.56 | 24035.0821 | 0 | 0 | 0 | 0 | 24035.0821 | 0.198% | 24031.54 | 3.5421
2917 | Union Business/Negotiations | 14016 | HR | 0.005 | HR | 70.08 | 1.88 | 0.8 | 29.8213 | 216.56 | 8072.6196 | 0 | 0 | 0 | 0 | 8072.6196 | 0.06649% | 8062.35 | 10.2696
|  | Lewis County - Planned for 2015 I: TOTALS:; Lewis County - Planned for 2015 K: 22983.904; Lewis County - Planned for 2015 M: 5629089.404; Lewis County - Planned for 2015 O: 3306153.0141; Lewis County - Planned for 2015 Q: 3206278.2995 | 12141520.7176 | 100% | 12141577.04

## 2015 Work Plan & Budget Sample
WORK PROGRAM AND BUDGET REPORT
COUNTY ROAD ADMINISTRATION BOARD
Maintenance Management Program
Planned for 2015
|  | C | D | E | F | H | I | J | K | L | M | N | O | P | Q | R | S
(COST DISTRIBUTION)
[6 empty] | ANNUAL | AVG |  |  | Labor |  | Equip |  | Material
| ACTIVITY |  |  | PLANNED |  | WORK | DAILY | CREW | PERSON | cost per |  | cost per |  | cost per | MATERIAL/ OTHER | TOTAL | Percent
CODE | NAME | INVENTORY |  | EFFORT LEVEL |  | QTY | PROD | SIZE | DAYS | crewday | LABOR | crewday | EQUIP | crewday |  | COST | of Total
|  | QTY | UNIT | QTY | UNIT | = ( C X E ) |  | = ( H / I ) X J |  |  | = ( H / I ) X L | = ( H / I ) X N |  | = ( H / I ) X P |  | = M+O+Q
2311 | GRADING | 1131 | miles | 8 | pass mi | 9048 | 12 | 1 | 754 | 230 | 173420 | 224 | 168896 | 0 | 0 | 342316 | 10.55%
2313 | RE-GRAVELING | 1131 | miles | 5 | cu yd | 5655 | 150 | 6 | 226.2 | 1274 | 48029.8 | 1032 | 38906.4 | 1800 | 67860 | 154796.2 | 4.769%
2321 | POTHOLE REPAIR | 648 | miles | 1 | ton | 648 | 2 | 2 | 648 | 458 | 148392 | 64 | 20736 | 80 | 25920 | 195048 | 6.009%
2322 | CRACK SEALING | 648 | miles | 5 | gal | 3240 | 24 | 3 | 405 | 687 | 92745 | 144 | 19440 | 218 | 29430 | 141615 | 4.363%
2323 | BLADE PATCHING | 648 | miles | 1 | ton | 648 | 75 | 10 | 86.4 | 1682 | 14532.48 | 1624 | 14031.36 | 5370 | 46396.8 | 74960.64 | 2.309%
2324 | SEAL COATING (BST) | 648 | miles | 0.2 | road mi | 129.6 | 3 | 21 | 907.2 | 3993 | 172497.6 | 3040 | 131328 | 8700 | 375840 | 679665.6 | 20.94%
2331 | SHOULDER BLADING | 1296 | miles | 0.4 | shld mi | 518.4 | 6 | 4 | 345.6 | 826 | 71366.4 | 536 | 46310.4 | 0 | 0 | 117676.8 | 3.625%
2332 | SHOULDER REPAIR | 1296 | miles | 0.5 | cu yd | 648 | 8 | 4 | 324 | 816 | 66096 | 480 | 38880 | 96 | 7776 | 112752 | 3.474%
2390 | OTHER ROAD MAINT | 1779 | miles | 1 | hours | 1779 | 16 | 2 | 222.375 | 358 | 39805.125 | 32 | 3558 | 0 | 0 | 43363.125 | 1.336%
2411 | DITCHING W/GRADER | 1296 | miles | 0.1 | ditch mi | 129.6 | 3 | 4 | 172.8 | 816 | 35251.2 | 496 | 21427.2 | 0 | 0 | 56678.4 | 1.746%
2412 | DITCHING W/DITCHER | 1296 | miles | 10 | ditch ft | 12960 | 500 | 6 | 155.52 | 1274 | 33022.08 | 880 | 22809.6 | 0 | 0 | 55831.68 | 1.72%
2421 | CULVERT CLEANING | 2669 | each | 1 | culverts | 2669 | 20 | 2 | 266.9 | 408 | 54447.6 | 32 | 4270.4 | 0 | 0 | 58718 | 1.809%
2422 | CULVERT REP/REPL | 2669 | each | 0.2 | lin ft | 533.8 | 40 | 6 | 80.07 | 1174 | 15667.03 | 680 | 9074.6 | 480 | 6405.6 | 31147.23 | 0.9596%
2490 | OTHER DRAINAGE MTCE | 1779 | miles | 1 | hours | 1779 | 16 | 2 | 222.375 | 408 | 45364.5 | 200 | 22237.5 | 0 | 0 | 67602 | 2.083%
2511 | BRIDGE/STRUCT MTCE | 124 | each | 0.5 | hours | 62 | 24 | 3 | 7.75 | 587 | 1516.4167 | 256 | 661.3333 | 50 | 129.1667 | 2306.9167 | 0.07107%
2512 | BRIDGE/STRUCT REPAIR | 124 | each | 0.3 | hours | 37.2 | 24 | 3 | 4.65 | 587 | 909.85 | 256 | 396.8 | 100 | 155 | 1461.65 | 0.04503%
2590 | OTHER BRG/STR MAINT | 124 | each | 0.25 | hours | 31 | 24 | 3 | 3.875 | 587 | 758.2083 | 256 | 330.6667 | 100 | 129.1667 | 1218.0417 | 0.03753%
2641 | SIGN MAINTENANCE | 45000 | each | 0.02 | hours | 900 | 24 | 2 | 75 | 458 | 17175 | 200 | 7500 | 100 | 3750 | 28425 | 0.8757%
2642 | GUARDRAIL REPAIR | 3240 | feet | 0.5 | lin ft | 1620 | 60 | 2 | 54 | 458 | 12366 | 100 | 2700 | 200 | 5400 | 20466 | 0.6305%
2643 | TRAFFIC MARKINGS | 1944 | miles | 1560 | ft | 3032640 | 10000 | 2 | 606.528 | 458 | 138894.912 | 100 | 30326.4 | 800 | 242611.2 | 411832.512 | 12.69%
2660 | SNOW & ICE CONTROL | 1779 | miles | 2.2 | hours | 3913.8 | 8 | 1 | 489.225 | 229 | 112032.525 | 100 | 48922.5 | 100 | 48922.5 | 209877.525 | 6.466%
2670 | STREET CLEANING | 1779 | miles | 1.3 | hours | 2312.7 | 32 | 4 | 289.0875 | 766 | 55360.2563 | 57 | 4119.4969 | 200 | 14454.375 | 73934.1281 | 2.278%
2690 | OTHER TRAFFIC MAINT | 1779 | miles | 0 | hours | 0 | 16 | 2 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
2712 | BRUSH CONTROL-MECH | 1296 | miles | 0.1 | shldr mi | 129.6 | 3 | 3 | 129.6 | 587 | 25358.4 | 125 | 5400 | 0 | 0 | 30758.4 | 0.9476%
2713 | BRUSH CONTROL-MANUAL | 1296 | miles | 1 | hours | 1296 | 48 | 4 | 108 | 1174 | 31698 | 53 | 1431 | 0 | 0 | 33129 | 1.021%
2721 | CHEM VEG CONTRL-MECH | 1296 | miles | 0.1 | shldr mi | 129.6 | 12 | 2 | 21.6 | 408 | 4406.4 | 333 | 3596.4 | 2400 | 25920 | 33922.8 | 1.045%
2722 | CHEM VEG CONTRL-MAN | 1296 | miles | 0 | hours | 0 | 16 | 2 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
2731 | LANDSCAPE MAINT | 1296 | miles | 1 | hours | 1296 | 32 | 4 | 162 | 736 | 29808 | 16 | 648 | 80 | 3240 | 33696 | 1.038%
2751 | LITTER CONTROL | 1296 | miles | 1 | hours | 1296 | 16 | 2 | 162 | 368 | 29808 | 16 | 1296 | 40 | 3240 | 34344 | 1.058%
2761 | SLOPE REPAIR | 1296 | miles | 0.7 | hours | 907.2 | 32 | 4 | 113.4 | 816 | 23133.6 | 55 | 1559.25 | 0 | 0 | 24692.85 | 0.7608%
2790 | OTHER ROADSIDE MAINT | 1296 | miles | 0 | hours | 0 | 32 | 4 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
2910 | MAINTENANCE ADMIN | 1 | year | 5600 | hours | 5600 | 8 | 1 | 700 | 248 | 173600 | 0 | 0 | 0 | 0 | 173600 | 5.348%
|  | Planned for 2015 I: TOTALS:; Planned for 2015 K: 7743.1555; Planned for 2015 M: 1667462.3832; Planned for 2015 O: 670793.3069; Planned for 2015 Q: 907579.8083 | 3245835.4985 | 100%

## 2015 WP&B sample with Percent
WORK PROGRAM AND BUDGET REPORT
COUNTY ROAD ADMINISTRATION BOARD
Maintenance Management Program
Planned for 2014
|  | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S
(COST DISTRIBUTION)
[7 empty] | ANNUAL | AVG |  |  | Labor |  | Equip |  | Material
| ACTIVITY |  |  | PLANNED |  | PERCENT | WORK | DAILY | CREW | PERSON | cost per |  | cost per |  | cost per | MATERIAL/ OTHER | TOTAL | Percent
CODE | NAME | INVENTORY |  | EFFORT LEVEL |  | OF PLAN | QTY | PROD | SIZE | DAYS | crewday | LABOR | crewday | EQUIP | crewday |  | COST | of Total
|  | QTY | UNIT | QTY | UNIT |  | = ( C X E )XG |  | = ( H / I ) X J |  |  | = ( H / I ) X L | = ( H / I ) X N |  | = ( H / I ) X P |  | = M+O+Q
2311 | GRADING | 1131 | miles | 8 | pass mi | 100% | 9048 | 12 | 1 | 754 | 230 | 173420 | 224 | 168896 | 0 | 0 | 342316 | 10.55%
2313 | RE-GRAVELING | 1131 | miles | 5 | cu yd | 100% | 5655 | 150 | 6 | 226.2 | 1274 | 48029.8 | 1032 | 38906.4 | 1800 | 67860 | 154796.2 | 4.769%
2321 | POTHOLE REPAIR | 648 | miles | 1 | ton | 100% | 648 | 2 | 2 | 648 | 458 | 148392 | 64 | 20736 | 80 | 25920 | 195048 | 6.009%
2322 | CRACK SEALING | 648 | miles | 5 | gal | 100% | 3240 | 24 | 3 | 405 | 687 | 92745 | 144 | 19440 | 218 | 29430 | 141615 | 4.363%
2323 | BLADE PATCHING | 648 | miles | 1 | ton | 100% | 648 | 75 | 10 | 86.4 | 1682 | 14532.48 | 1624 | 14031.36 | 5370 | 46396.8 | 74960.64 | 2.309%
2324 | SEAL COATING (BST) | 648 | miles | 0.2 | road mi | 100% | 129.6 | 3 | 21 | 907.2 | 3993 | 172497.6 | 3040 | 131328 | 8700 | 375840 | 679665.6 | 20.94%
2331 | SHOULDER BLADING | 1296 | miles | 0.4 | shld mi | 100% | 518.4 | 6 | 4 | 345.6 | 826 | 71366.4 | 536 | 46310.4 | 0 | 0 | 117676.8 | 3.625%
2332 | SHOULDER REPAIR | 1296 | miles | 0.5 | cu yd | 100% | 648 | 8 | 4 | 324 | 816 | 66096 | 480 | 38880 | 96 | 7776 | 112752 | 3.474%
2390 | OTHER ROAD MAINT | 1779 | miles | 1 | hours | 100% | 1779 | 16 | 2 | 222.375 | 358 | 39805.125 | 32 | 3558 | 0 | 0 | 43363.125 | 1.336%
2411 | DITCHING W/GRADER | 1296 | miles | 0.1 | ditch mi | 100% | 129.6 | 3 | 4 | 172.8 | 816 | 35251.2 | 496 | 21427.2 | 0 | 0 | 56678.4 | 1.746%
2412 | DITCHING W/DITCHER | 1296 | miles | 10 | ditch ft | 100% | 12960 | 500 | 6 | 155.52 | 1274 | 33022.08 | 880 | 22809.6 | 0 | 0 | 55831.68 | 1.72%
2421 | CULVERT CLEANING | 2669 | each | 1 | culverts | 100% | 2669 | 20 | 2 | 266.9 | 408 | 54447.6 | 32 | 4270.4 | 0 | 0 | 58718 | 1.809%
2422 | CULVERT REP/REPL | 2669 | each | 0.2 | lin ft | 100% | 533.8 | 40 | 6 | 80.07 | 1174 | 15667.03 | 680 | 9074.6 | 480 | 6405.6 | 31147.23 | 0.9596%
2490 | OTHER DRAINAGE MTCE | 1779 | miles | 1 | hours | 100% | 1779 | 16 | 2 | 222.375 | 408 | 45364.5 | 200 | 22237.5 | 0 | 0 | 67602 | 2.083%
2511 | BRIDGE/STRUCT MTCE | 124 | each | 0.5 | hours | 100% | 62 | 24 | 3 | 7.75 | 587 | 1516.4167 | 256 | 661.3333 | 50 | 129.1667 | 2306.9167 | 0.07107%
2512 | BRIDGE/STRUCT REPAIR | 124 | each | 0.3 | hours | 100% | 37.2 | 24 | 3 | 4.65 | 587 | 909.85 | 256 | 396.8 | 100 | 155 | 1461.65 | 0.04503%
2590 | OTHER BRG/STR MAINT | 124 | each | 0.25 | hours | 100% | 31 | 24 | 3 | 3.875 | 587 | 758.2083 | 256 | 330.6667 | 100 | 129.1667 | 1218.0417 | 0.03753%
2641 | SIGN MAINTENANCE | 45000 | each | 0.02 | hours | 100% | 900 | 24 | 2 | 75 | 458 | 17175 | 200 | 7500 | 100 | 3750 | 28425 | 0.8757%
2642 | GUARDRAIL REPAIR | 3240 | feet | 0.5 | lin ft | 100% | 1620 | 60 | 2 | 54 | 458 | 12366 | 100 | 2700 | 200 | 5400 | 20466 | 0.6305%
2643 | TRAFFIC MARKINGS | 1944 | miles | 1560 | ft | 100% | 3032640 | 10000 | 2 | 606.528 | 458 | 138894.912 | 100 | 30326.4 | 800 | 242611.2 | 411832.512 | 12.69%
2660 | SNOW & ICE CONTROL | 1779 | miles | 2.2 | hours | 100% | 3913.8 | 8 | 1 | 489.225 | 229 | 112032.525 | 100 | 48922.5 | 100 | 48922.5 | 209877.525 | 6.466%
2670 | STREET CLEANING | 1779 | miles | 1.3 | hours | 100% | 2312.7 | 32 | 4 | 289.0875 | 766 | 55360.2563 | 57 | 4119.4969 | 200 | 14454.375 | 73934.1281 | 2.278%
2690 | OTHER TRAFFIC MAINT | 1779 | miles | 0 | hours | 100% | 0 | 16 | 2 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
2712 | BRUSH CONTROL-MECH | 1296 | miles | 0.1 | shldr mi | 100% | 129.6 | 3 | 3 | 129.6 | 587 | 25358.4 | 125 | 5400 | 0 | 0 | 30758.4 | 0.9476%
2713 | BRUSH CONTROL-MANUAL | 1296 | miles | 1 | hours | 100% | 1296 | 48 | 4 | 108 | 1174 | 31698 | 53 | 1431 | 0 | 0 | 33129 | 1.021%
2721 | CHEM VEG CONTRL-MECH | 1296 | miles | 0.1 | shldr mi | 100% | 129.6 | 12 | 2 | 21.6 | 408 | 4406.4 | 333 | 3596.4 | 2400 | 25920 | 33922.8 | 1.045%
2722 | CHEM VEG CONTRL-MAN | 1296 | miles | 0 | hours | 100% | 0 | 16 | 2 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
2731 | LANDSCAPE MAINT | 1296 | miles | 1 | hours | 100% | 1296 | 32 | 4 | 162 | 736 | 29808 | 16 | 648 | 80 | 3240 | 33696 | 1.038%
2751 | LITTER CONTROL | 1296 | miles | 1 | hours | 100% | 1296 | 16 | 2 | 162 | 368 | 29808 | 16 | 1296 | 40 | 3240 | 34344 | 1.058%
2761 | SLOPE REPAIR | 1296 | miles | 0.7 | hours | 100% | 907.2 | 32 | 4 | 113.4 | 816 | 23133.6 | 55 | 1559.25 | 0 | 0 | 24692.85 | 0.7608%
2790 | OTHER ROADSIDE MAINT | 1296 | miles | 0 | hours | 100% | 0 | 32 | 4 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0%
2910 | MAINTENANCE ADMIN | 1 | year | 5600 | hours | 100% | 5600 | 8 | 1 | 700 | 248 | 173600 | 0 | 0 | 0 | 0 | 173600 | 5.348%
|  | Planned for 2014 I: TOTALS:; Planned for 2014 K: 7743.1555; Planned for 2014 M: 1667462.3832; Planned for 2014 O: 670793.3069; Planned for 2014 Q: 907579.8083 | 3245835.4985 | 100%